## KT-Plan
KT Plan for 2 Weeks
S.NO | Date | Process | Description | Key Points | Status
1 | 2019-11-18 | Infrastructure View | Servers, DB's and Installed Products & its versions in both UAT & PRODUCTION | Shared | Completed
2 |  | Brief Overview of all Processes | Introduction to the respective SPOCs | Shared | Completed
3 |  | AP | Employee Reimbursements & it's masters | Shared | Completed
4 | 2019-11-19 | SP Process | Statutory Payments RFA creation - workflow | Shared | Completed
5 |  |  | Approval Matrix maintenance & providing new user into SP Process | Shared | Completed
6 |  | TC Process | Trial Coil process workflow | Shared | Completed
7 | 2019-11-20 | HelpDesk Process | Helpdesk workflow & it's masters | Shared | Completed
8 |  | Letter Repository | Compliance & Repository workflow & it's masters | Shared | Completed
9 |  | Conference Room Booking | Conference Room Booking workflow | Shared | Completed
10 | 2019-11-21 | Guest House Booking | Guest House Booking WI Initiation & Workflow | Shared | Completed
11 |  | Cab Request | Cab Request WI Initiation & Workflow | Shared | Completed
12 |  | VPF Contribution | VPF Contribution Workflow & masters | Shared | Completed
13 | 2019-11-22 | Vendor Portal/Trail Coil Portal | Implemention of Vendor Portal like Configuration, Coding guidelines | Shared | Completed
14 |  | Form-19 Portal | Workflow & masters | Shared | Completed

## Overview
Below are the processes are Completed the development & are in LIVE.
S.NO | Process | Description | LIVE | UAT | Author | Server IP Address |  | Status | Pending points/Description
[6 empty] | LIVE | UAT & DB Server
1 | AP | Employee Reimbursements | YES | YES | Nanjunda Moorthy | 172.16.8.97 | 172.16.8.81 | Working fine | working in UAT with some changes related to SFIC & ASFI company code
2 | SP | Statutory Payments | YES | YES | Harinatha R | 172.16.8.97 | 172.16.8.81 | Working fine | No changes
3 | TC | Trial Coil | YES | YES | Harinatha R | 172.16.8.97 | 172.16.8.81 | Working fine | No changes
4 | HelpDesk | HelpDesk | YES | YES | Sivashanakr KS | 172.16.8.97 | 172.16.8.81 | Working fine | This to be extended to Admin team
5 | LR | Compliance and Repository | YES | YES | Sivashankar KS | 172.16.8.97 | 172.16.8.81 | Working fine | Phase-2 development is pending
6 | Conference Room Booking | Conference Room Booking | YES | YES | Sivashankar KS | 172.16.8.97 | 172.16.8.81 | Working fine | Phase-2 development is pending
7 | GHB | Guest House Booking | YES | YES | Sivashankar KS | 172.16.8.97 | 172.16.8.81 | Working fine | Phase-2 development(Billing part) is pending
8 | CabRequest | Cab Request | NO | YES | Sivashankar KS | 172.16.8.97 | 172.16.8.81 | Testing in UAT | Need to be worked on some new changes
9 | Vendor Portal | Vendor Portal Implementation | YES | YES | Sivashankar KS | 172.16.8.96 | 172.16.8.80 | Working fine | No changes
10 | Trail Coil Portal | Vendor Portal Extension | YES | YES | Sivashanakr KS | 172.16.8.96 | 172.16.8.80 | Working fine | No changes
11 | Form-19 Portal | For Ex Brit Employees | YES | YES | Sivashankar KS | 172.16.8.96 | 172.16.8.80 | Working fine | Phase-2 development(workflow inbetween HR and PF Teams) is pending
12 | VPF-Contribution | Employes to contribute their VPF. | YES | YES | Sivashankar KS | 172.16.8.97 | 172.16.8.81 | Working fine | No changes
Pending developments
S.NO | Description | Effort Estimation with man days
1 | AP Process changes w.r to SFIC & ASFI | 10 mandatory dates as per the received requirement
2 | Cab Request development | 15 mandatory dates as per the received requirement
3 | HelpDesk process Extending to Admin team | 15 mandatory dates including development, deployment and testing in both UAT & PRD
4 | LR(Compliance and Repository) Phase-2 | 2-3 weeks
5 | Conference Room Booking Phase-2 | 2-3 Weeks
6 | Guest House Booking Billing part | 1 month
7 | Form-19 Portal Phase-2 development | 1 month
8 | JV Process development | Not yet discussed
9 | My Profile development | Not yet discussed

## Infrastructure
PRODUCTION SERVER DETAILS - 172.16.8.97
S.NO | Application Details | Description | Path
1 | Server details | Windows server 2012R2
2 | Java | Java 1.7.0 | C:\Program Files\Java\jdk1.7.0_79
3 | JBOSS details | jboss-eap-6.3 | D:\Newgen\jboss-eap-6.3
3 | Database and Version details | MSSQL 2012 | 2012
4 | iBPS Version | iBPS 3.0 Standard Version | D:\Newgen\iBPS 3.0
5 | OmniDocs Version | OmniDocs 8.3 | D:\Newgen\OmniDocs8.3
6 | OF Services
7 | SMS Path |  | D:\Newgen\OmniDocs8.3\Common Services for J2EE\SMS
8 | Wrapper Path |  | D:\Newgen\OmniDocs8.3\Wrapper
9 | Windows services Configured For | All | JBOSS,SMS,WRAPPER,LDAP,OpenOffice
10 | Logs |  | D:\Newgen\jboss-eap-6.3\bin\ProcessName_Logs
UAT SERVER DETAILS - 172.16.8.81
S.NO | Application Details | Description | Path
1 | Server details | Windows server 2012R2
2 | Java | Java 1.8.0_91 | C:\Program Files\Java\jdk1.8.0_91
3 | JBOSS details | jboss-eap-7.1 | D:\Newgen\jboss-eap-7.1
3 | Database and Version details | MSSQL 2012 | 2012
4 | iBPS Version | iBPS 4.0 updated patches till Hotfix_iBPS_4.0_192 | D:\Newgen\iBPS 4.0
5 | OmniDocs Version | OmniDocs10.0 | D:\Newgen\OmniDocs10.0
6 | OF Services
7 | SMS Path |  | D:\Newgen\OmniDocs10.0\Common Services for J2EE\SMS
8 | Wrapper Path |  | D:\Newgen\OmniDocs10.0\Wrapper
9 | Windows services Configured For | All | JBOSS,SMS,WRAPPER,LDAP,OpenOffice
10 | Logs |  | D:\Newgen\jboss-eap-7.1\bin\ProcessName_Logs

## Introduction-Britannia
S.No | Name | Process Name | Extension | Department | Consult For
1 | Nagarajan.v | IT Head | 7411 | IT Manager | IT Team
2 | Varalakshmi | IT Manager | 7358
3 | Sivaram Prasad | AP Process and VPF-Contribution Owner | 7203 | Finance Head | AP Process
4 | Jestus | AP Process | 7208 | Finance Team
5 | Vijaya Lakshmi | AP Process - SSC Lead | 7277
6 | Avinash babu | AP Process - member | 7561
7 | Quality Room |  | 7318
8 | Vishal | AP Process - member | 7420
9 | Mounika | AP Process - member | 7386
11 | Arundhathi Sahu | Trial Coil Manager | 7184 | Purchase Manager | TC Process
12 | KARAMALA VIGNESHACHARI | Trial Coil - member | 7362
13 | S.N. Khannan | SP Process - Owner | 7522 | Taxation Head
14 | Shirisha | HR SPOC (AP, HelpDesk Owner, LR Owne and Form-19) | 7165 | HR Team | HR Team
16 | Monika P HR | Form-19 and AP | 7385
17 | 17th Floor Reception |  | 7199 | Reception | Reception
18 | 16th Floor Reception |  | 7259
19 | EO IT Help Desk |  | 7262 | Help Desk | Help Desk
20 |  |  | 7263
21 |  |  | 7265
22 | Kolkatta HelpDesk |  | 223000
23 | Delhi Helpdesk |  | 113078
24 | Mumbari HelpDesk |  | 223000
25 | Ravi |  | 7489 | LNDEV | iBPS Support
26 | Revathi |  | 7543
29 | Girish | AP Process SAP parking & posting Issues | 7449 | SAP Support FI
31 | Vara Prasad/Praveena | SAP HR Team(All Processes) | 7425 | SAP HR Support
32 | Mohan | SAP Access support | 7565 | SAP Access/ Unlock
33 | Wintel Team | Network Issues and HP Server maintenance | 7260 | Wintel Team | Wintel Team
34 | Raghava |  | 7979 | Wintel Team
35 | Vijay | Form-19 | 7218 | PF Team | PF Team
30 | Roopa | GHB and Cab Request Owners | 7158 | Admin Team | Admin Team
31 | Veena |  | 7157